## Projected
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly
Record prototype | bar: WK13
Upload VIVA | bar: WK14
Submit report | bar: WK14
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report | bar: WK11 to WK12
Literature Review
Review datasets
Review algorithms
Finalise section in report | bar: WK10 to WK12
Prototype
Design
Construct
Create custom dataset
Tweek prototype | bar: WK7
Generate evaluation results | bar: WK8 to WK9
Discussion of Results
Write prototype evaluation | bar: WK10 to WK11
Write dataset evaluation | bar: WK10 to WK11
Write hypothesis testing | bar: WK11 to WK12
Write project evaluation | bar: WK11 to WK12
Finalise section in report | bar: WK11 to WK12
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK12
Finalise Introduction | bar: WK12
Finalise Abstract | bar: WK12

## Actual
|  | 15th Feb | 22nd Feb | 1st Mar | 8th Mar | 15th Mar | 22nd Mar | 29th Mar | 12th Apr | 19th Apr | 26th Apr | 3rd May | 10th May | 17th May | 24th May | 31st May
WP | Task | Wk1 | Wk2 | Wk3 | WK4 | WK5 | WK6 | Easter | WK7 | WK8 | WK9 | WK10 | WK11 | WK12 | WK13 | WK14
Report
Create an account
Load template
Read guidelines
Deliverables
Create GIT Account
Share with lecturer
Commit regularly | bar: WK8; WK14
Record prototype | bar: WK14
Upload VIVA | bar: WK14
Submit report | bar: WK14
Research Methodology
Hypothesis
Research Questions
Research Methods
Research Pipeline
Finalise section in report | bar: WK9
Literature Review
Review Methodologies
Review algorithms
Finalise section in report | bar: WK10
Prototype
Design
Construct
Create custom dataset
Tweek prototype | bar: WK8
Generate evaluation results | bar: WK8 to WK10
Discussion of Results | bar: WK11
Write prototype evaluation | bar: WK11
Write dataset evaluation | bar: WK11
Write hypothesis testing | bar: WK11
Write project evaluation | bar: WK12
Finalise section in report | bar: WK14
Other sections (Conclusion, Introduction, Abstract)
Finalise conclusion & recommendations | bar: WK10
Finalise Introduction | bar: WK10
Finalise Abstract | bar: WK10